## Estimate
Bulk materials
|  | Staff | Labour | Plant | Concrete | Steel | Other | Subcon | Other | TOTAL
| Sunk costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6374775 | 6374775
A0000 | Initial design | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1568726 | 1568726
A0000 | Detailed design (70%) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2126023 | 2126023
A0000 | Consulting fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 101708 | 101708
A0000 | Environmental and community consultations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2578318 | 2578318
| Provisions | 0 | 153863 | 146669 | 1808144 | 0 | 0 | 0 | 820776 | 2929452
P1010 | Onsite rework of reinforcing | 0 | 143834 | 39785 | 0 | 0 | 0 | 0 | 0 | 183619
P1020 | Corrosion protection | 0 | 0 | 0 | 1808144 | 0 | 0 | 0 | 0 | 1808144
P1030 | Inclement weather | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 372100 | 372100
P1040 | Delay costs | 0 | 10029 | 106884 | 0 | 0 | 0 | 0 | 0 | 116913
P1050 | Bank guarantees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 448676 | 448676
| Establishment and preliminaries | 6122832 | 139528 | 745513 | 443 | 0 | 457686 | 669281 | 1083692 | 9218975
| Cable relocation | 0 | 0 | 0 | 0 | 0 | 0 | 320659 | 0 | 320659
J1020 | Cable and connections | 0 | 0 | 0 | 0 | 0 | 0 | 211451 | 0 | 211451
J1030 | Remove existing cabling | 0 | 0 | 0 | 0 | 0 | 0 | 109208 | 0 | 109208
| Site establishment | 8829 | 83777 | 69473 | 443 | 0 | 137686 | 263806 | 0 | 564014
A2400 | Mobilise site office 1 | 0 | 2647 | 1567 | 244 | 0 | 35985 | 37921 | 0 | 78364
A2400 | Mobilise site office 2 | 0 | 23106 | 22542 | 199 | 0 | 95961 | 70220 | 0 | 212028
A2300 | Site offices | 0 | 0 | 3892 | 0 | 0 | 0 | 0 | 0 | 3892
A2300 | Site offices 1 | 0 | 0 | 8752 | 0 | 0 | 0 | 0 | 0 | 8752
A2300 | Site offices 2 | 0 | 0 | 2547 | 0 | 0 | 0 | 0 | 0 | 2547
A2100 | Site supervisor | 8829 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8829
E2001 | Safety zones | 0 | 5761 | 733 | 0 | 0 | 2214 | 0 | 0 | 8708
E2002 | Set up environmental controls | 0 | 5626 | 655 | 0 | 0 | 1438 | 0 | 0 | 7719
E6010 | Soil testing | 0 | 1285 | 294 | 0 | 0 | 0 | 155665 | 0 | 157244
E6020 | Initial earthworks | 0 | 45352 | 28491 | 0 | 0 | 2088 | 0 | 0 | 75931
| Management | 2062854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2062854
A1000 | Project manager | 620080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620080
A2110 | Project administrator | 50876 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50876
A2120 | Project administrator | 56748 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56748
A2100 | Design liaison | 54502 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54502
A1000 | Project office | 195814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 195814
A2190 | Site personnel | 133825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133825
A1000 | Project office | 381275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 381275
A2000 | Safety management | 35211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35211
A2150 | Site personnel | 184541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184541
A2160 | Site personnel | 235476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235476
A2170 | Site personnel | 16746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16746
A2180 | Site personnel | 97760 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 97760
| Construction management | 3342474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3342474
A2100 | Construction manager | 506632 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506632
A1000 | Deputy construction manager | 319125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 319125
A1000 | Construction engineer | 259741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 259741
A2110 | Site personnel | 321013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321013
A2120 | Site personnel | 212927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 212927
A2130 | Site personnel | 107108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107108
A2140 | Site personnel | 397298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 397298
A2115 | Construction supervisor | 163487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163487
A2125 | Construction supervisor | 147805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147805
A2100 | Foreman | 95486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 95486
A1000 | Project engineer | 268382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 268382
A2100 | Site engineer | 178407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178407
A2100 | Superintendent | 184523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184523
A2100 | Foreman | 180540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180540
| Surveying | 708675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 708675
A2100 | Surveyors | 498580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498580
A2100 | Survey office | 210095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 210095
| Staff accommodation and vehicles | 0 | 0 | 250326 | 0 | 0 | 90023 | 0 | 842319 | 1182668
A2000 | Staff relocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34202 | 34202
A3000 | Staff vehicles | 0 | 0 | 250326 | 0 | 0 | 90023 | 0 | 30927 | 371276
A4000 | Staff accommodation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 777190 | 777190
| Site facilities | 0 | 55751 | 425714 | 0 | 0 | 229977 | 84816 | 241373 | 1037631
A2300 | Site offices North | 0 | 0 | 72936 | 0 | 0 | 0 | 0 | 0 | 72936
A2300 | Site offices South | 0 | 0 | 165102 | 0 | 0 | 0 | 0 | 0 | 165102
A2300 | Site offices Area 3 | 0 | 0 | 44816 | 0 | 0 | 0 | 0 | 0 | 44816
A2400 | IT systems | 0 | 0 | 89575 | 0 | 0 | 3014 | 55386 | 11548 | 159523
A2500 | Site services | 0 | 0 | 11459 | 0 | 0 | 143984 | 26264 | 3813 | 185520
A2500 | Surveying consumables | 0 | 0 | 0 | 0 | 0 | 35708 | 0 | 0 | 35708
A2500 | Office expenses | 0 | 0 | 23452 | 0 | 0 | 28135 | 0 | 0 | 51587
A2000 | Training - OHS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226012 | 226012
A2300 | Site offices | 0 | 55751 | 18374 | 0 | 0 | 19136 | 3166 | 0 | 96427
| Direct costs | 2335738 | 10500017 | 4110275 | 3093288 | 4973734 | 6295248 | 6141234 | 450940 | 37900474
| Area 1 | 2335738 | 3519547 | 2355301 | 64613 | 0 | 1044428 | 2616203 | 449451 | 12385281
| Design | 2103961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103961
A1000 | Project office | 508790 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 508790
A3000 | Permanent works design | 1282997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1282997
A2100 | Construction facilities design | 125085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125085
A2200 | Geotechnical consultant | 136796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136796
A2200 | Ground testing | 22159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22159
A2100 | Concrete testing | 28134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28134
| Special plant | 0 | 2277480 | 1719349 | 0 | 0 | 499255 | 0 | 0 | 4496084
A2400 | Large cranes | 0 | 1399424 | 855403 | 0 | 0 | 376734 | 0 | 0 | 2631561
A2310 | Small plant | 0 | 11798 | 11752 | 0 | 0 | 6128 | 0 | 0 | 29678
A2320 | Small plant | 0 | 102900 | 177810 | 0 | 0 | 0 | 0 | 0 | 280710
A2500 | Mobile cranes | 0 | 208600 | 148910 | 0 | 0 | 18153 | 0 | 0 | 375663
A2300 | Small plant | 0 | 59957 | 82731 | 0 | 0 | 0 | 0 | 0 | 142688
A2600 | General purpose cranes | 0 | 494801 | 442743 | 0 | 0 | 98240 | 0 | 0 | 1035784
| Site equipment | 0 | 868124 | 472976 | 0 | 0 | 165435 | 10522 | 449451 | 1966508
A2400 | Consumables and small tools | 0 | 99921 | 88173 | 0 | 0 | 47235 | 0 | 0 | 235329
A2300 | Mobilise and demobilise small plant | 0 | 5808 | 4881 | 0 | 0 | 0 | 0 | 0 | 10689
A2300 | Small plant | 0 | 9097 | 241097 | 0 | 0 | 102024 | 0 | 0 | 352218
A2200 | Plant support and maintenance | 0 | 753298 | 138825 | 0 | 0 | 16176 | 10522 | 74515 | 993336
A2100 | Crew accommodation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 374936 | 374936
| Environmental management | 231777 | 30299 | 0 | 0 | 0 | 62559 | 0 | 0 | 324635
A2100 | Site personnel | 231777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231777
A2400 | Environmental management | 0 | 30299 | 0 | 0 | 0 | 62559 | 0 | 0 | 92858
| Stormwater drainage | 0 | 2418 | 1341 | 12523 | 0 | 885 | 108691 | 0 | 125858
C1100 | Pipe outlets | 0 | 0 | 0 | 0 | 0 | 0 | 50104 | 0 | 50104
D1040 | Demolition | 0 | 0 | 0 | 0 | 0 | 0 | 10283 | 0 | 10283
C1120 | Kerb A | 0 | 801 | 383 | 7458 | 0 | 384 | 3166 | 0 | 12192
C1130 | Kerb B | 0 | 1617 | 958 | 5065 | 0 | 501 | 6940 | 0 | 15081
C1140 | Pipe outlets A | 0 | 0 | 0 | 0 | 0 | 0 | 19564 | 0 | 19564
C1150 | Pipe outlets B | 0 | 0 | 0 | 0 | 0 | 0 | 18634 | 0 | 18634
| Earthworks | 0 | 191007 | 143782 | 0 | 0 | 0 | 799445 | 0 | 1134234
E2003 | Bulk earthworks | 0 | 0 | 0 | 0 | 0 | 0 | 11679 | 0 | 11679
E1011 | Rock removal North A | 0 | 0 | 0 | 0 | 0 | 0 | 109476 | 0 | 109476
E1012 | Rock removal South A | 0 | 0 | 0 | 0 | 0 | 0 | 254377 | 0 | 254377
E1021 | Bulk earthworks | 0 | 169216 | 121523 | 0 | 0 | 0 | 0 | 0 | 290739
E1023 | Drainage excavation | 0 | 19972 | 20369 | 0 | 0 | 0 | 0 | 0 | 40341
E1027 | Bulk earthworks | 0 | 0 | 0 | 0 | 0 | 0 | 27370 | 0 | 27370
E1013 | Rock removal North B | 0 | 0 | 0 | 0 | 0 | 0 | 220033 | 0 | 220033
E1014 | Rock removal South B | 0 | 0 | 0 | 0 | 0 | 0 | 68240 | 0 | 68240
E1015 | Rock removal Area 3 | 0 | 0 | 0 | 0 | 0 | 0 | 108270 | 0 | 108270
E1025 | Corridor cut | 0 | 1819 | 1890 | 0 | 0 | 0 | 0 | 0 | 3709
| Shotcreting | 0 | 0 | 0 | 0 | 0 | 0 | 919039 | 0 | 919039
K1010 | Trimming | 0 | 0 | 0 | 0 | 0 | 0 | 68336 | 0 | 68336
K1020 | Dowel placement | 0 | 0 | 0 | 0 | 0 | 0 | 190211 | 0 | 190211
K1030 | Mesh placement | 0 | 0 | 0 | 0 | 0 | 0 | 48616 | 0 | 48616
K1050 | Shotcrete | 0 | 0 | 0 | 0 | 0 | 0 | 516367 | 0 | 516367
K1060 | Rockbolting | 0 | 0 | 0 | 0 | 0 | 0 | 95509 | 0 | 95509
| Retaining walls | 0 | 128223 | 1079 | 52090 | 0 | 277397 | 269276 | 0 | 728065
W1010 | South pathway support | 0 | 0 | 0 | 0 | 0 | 99398 | 0 | 0 | 99398
W1070 | Backfill | 0 | 0 | 0 | 0 | 0 | 0 | 74673 | 0 | 74673
W1020 | North pathway support | 0 | 0 | 0 | 0 | 0 | 97438 | 0 | 0 | 97438
W1030 | West retaining wall | 0 | 36973 | 209 | 11273 | 0 | 3608 | 0 | 0 | 52063
W1050 | North concrete wall | 0 | 91250 | 870 | 40817 | 0 | 6503 | 0 | 0 | 139440
W1040 | Improve existing retaining wall | 0 | 0 | 0 | 0 | 0 | 70450 | 0 | 0 | 70450
W1060 | Retained earth wall | 0 | 0 | 0 | 0 | 0 | 0 | 194603 | 0 | 194603
| Pavement | 0 | 17537 | 14298 | 0 | 0 | 38897 | 341038 | 0 | 411770
G1070 | Remove existing pavement | 0 | 6407 | 7584 | 0 | 0 | 0 | 0 | 0 | 13991
G1010 | Subgrade placement | 0 | 903 | 535 | 0 | 0 | 11221 | 269 | 0 | 12928
G1020 | Subbase placement | 0 | 5620 | 3390 | 0 | 0 | 15431 | 627 | 0 | 25068
G1030 | Base placement | 0 | 4607 | 2789 | 0 | 0 | 12245 | 482 | 0 | 20123
G1040 | Rotomilling | 0 | 0 | 0 | 0 | 0 | 0 | 6520 | 0 | 6520
G1050 | Tack coating | 0 | 0 | 0 | 0 | 0 | 0 | 3407 | 0 | 3407
G1060 | Wearing course | 0 | 0 | 0 | 0 | 0 | 0 | 108912 | 0 | 108912
G1080 | Membranes | 0 | 0 | 0 | 0 | 0 | 0 | 42570 | 0 | 42570
G1090 | Wearing course | 0 | 0 | 0 | 0 | 0 | 0 | 178251 | 0 | 178251
| Fencing | 0 | 0 | 0 | 0 | 0 | 0 | 84201 | 0 | 84201
W1080 | Access Track | 0 | 0 | 0 | 0 | 0 | 0 | 8700 | 0 | 8700
W1090 | Minor works South | 0 | 0 | 0 | 0 | 0 | 0 | 3679 | 0 | 3679
W1100 | Minor works North | 0 | 0 | 0 | 0 | 0 | 0 | 4140 | 0 | 4140
W1110 | Fencing South | 0 | 0 | 0 | 0 | 0 | 0 | 16585 | 0 | 16585
W1120 | Fencing North | 0 | 0 | 0 | 0 | 0 | 0 | 51097 | 0 | 51097
| Barriers | 0 | 4459 | 2476 | 0 | 0 | 0 | 83991 | 0 | 90926
S1140 | Guard rail removal | 0 | 0 | 0 | 0 | 0 | 0 | 4453 | 0 | 4453
D1030 | Demolition | 0 | 2155 | 1193 | 0 | 0 | 0 | 0 | 0 | 3348
C1080 | Infill concrete | 0 | 0 | 0 | 0 | 0 | 0 | 23461 | 0 | 23461
C1090 | Crash barrier | 0 | 2304 | 1283 | 0 | 0 | 0 | 0 | 0 | 3587
S1150 | Guardrail | 0 | 0 | 0 | 0 | 0 | 0 | 30550 | 0 | 30550
S1170 | Jersey barriers Stage 1 | 0 | 0 | 0 | 0 | 0 | 0 | 16788 | 0 | 16788
S1180 | Jersey barriers Stage 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2016 | 0 | 2016
S1190 | Jersey barriers Stage 3 | 0 | 0 | 0 | 0 | 0 | 0 | 6723 | 0 | 6723
| Paths | 0 | 1662905 | 1081370 | 7296 | 67272 | 1430229 | 192088 | 0 | 4441160
| Shared path North | 0 | 9721 | 516 | 740 | 0 | 22660 | 6257 | 0 | 39894
C2028 | Pathway | 0 | 1690 | 0 | 740 | 0 | 20538 | 6257 | 0 | 29225
E3001 | Detailed earthworks | 0 | 1565 | 516 | 0 | 0 | 2035 | 0 | 0 | 4116
S1080 | Cycle access guard rail | 0 | 6466 | 0 | 0 | 0 | 87 | 0 | 0 | 6553
| Shared path South | 0 | 2975 | 307 | 234 | 0 | 6589 | 1940 | 0 | 12045
C2028 | Pathway | 0 | 553 | 0 | 234 | 0 | 5690 | 1940 | 0 | 8417
E3001 | Detailed earthworks | 0 | 650 | 307 | 0 | 0 | 869 | 0 | 0 | 1826
S1080 | Cycle access guard rail | 0 | 1772 | 0 | 0 | 0 | 30 | 0 | 0 | 1802
| Pedestrian areas North | 0 | 5055 | 0 | 0 | 0 | 38281 | 0 | 0 | 43336
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 38211 | 0 | 0 | 38211
S1050 | Pedestrian handrail erection | 0 | 5055 | 0 | 0 | 0 | 70 | 0 | 0 | 5125
| Pedestrian areas South 1 | 0 | 8649 | 0 | 0 | 0 | 87957 | 0 | 0 | 96606
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 87838 | 0 | 0 | 87838
S1050 | Pedestrian handrail erection | 0 | 8649 | 0 | 0 | 0 | 119 | 0 | 0 | 8768
| Pedestrian areas South 2 | 0 | 1947 | 0 | 0 | 0 | 15322 | 0 | 0 | 17269
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 15297 | 0 | 0 | 15297
S1050 | Pedestrian handrail erection | 0 | 1947 | 0 | 0 | 0 | 25 | 0 | 0 | 1972
| Boardwalk and lookout | 0 | 41521 | 0 | 0 | 67272 | 102583 | 72950 | 0 | 284326
H1130 | Small diameter piles | 0 | 0 | 0 | 0 | 0 | 0 | 23279 | 0 | 23279
C2050 | Pipes | 0 | 0 | 0 | 0 | 0 | 0 | 33107 | 0 | 33107
C1063 | Piers | 0 | 0 | 0 | 0 | 0 | 0 | 16564 | 0 | 16564
S2100 | Minor reinforcing | 0 | 4661 | 0 | 0 | 8460 | 0 | 0 | 0 | 13121
S1060 | Joist fittings | 0 | 0 | 0 | 0 | 58812 | 0 | 0 | 0 | 58812
L1040 | Timber decks | 0 | 27546 | 0 | 0 | 0 | 102436 | 0 | 0 | 129982
S1080 | Cycle access guard rail | 0 | 9314 | 0 | 0 | 0 | 147 | 0 | 0 | 9461
| Signs and linemarking | 0 | 0 | 0 | 0 | 0 | 0 | 37825 | 0 | 37825
M1010 | Line marking | 0 | 0 | 0 | 0 | 0 | 0 | 5770 | 0 | 5770
M1030 | Pedestrian crossings | 0 | 0 | 0 | 0 | 0 | 0 | 3253 | 0 | 3253
M1040 | Cycle path marking | 0 | 0 | 0 | 0 | 0 | 0 | 3633 | 0 | 3633
M1050 | Warning signs | 0 | 0 | 0 | 0 | 0 | 0 | 25169 | 0 | 25169
| Landscaping | 0 | 6552 | 2861 | 0 | 0 | 24028 | 25370 | 0 | 58811
L1010 | Topsoil replacement North | 0 | 1402 | 535 | 0 | 0 | 11566 | 0 | 0 | 13503
L1020 | Topsoil replacement South | 0 | 5150 | 2326 | 0 | 0 | 12462 | 0 | 0 | 19938
L1030 | Seeding | 0 | 0 | 0 | 0 | 0 | 0 | 25370 | 0 | 25370
| Access track and surrounds | 0 | 1586485 | 1077686 | 6322 | 0 | 1132809 | 47746 | 0 | 3851048
D1010 | Clearing and grubbing | 0 | 69647 | 38711 | 0 | 0 | 0 | 0 | 0 | 108358
E4011 | Bulk earthworks | 0 | 136734 | 85115 | 0 | 0 | 0 | 0 | 0 | 221849
E4020 | Detailed earthworks | 0 | 1140826 | 823050 | 0 | 0 | 0 | 0 | 0 | 1963876
E4030 | Geotextile | 0 | 24899 | 5076 | 0 | 0 | 32832 | 0 | 0 | 62807
E5010 | Install rock South | 0 | 33658 | 20462 | 0 | 0 | 485895 | 0 | 0 | 540015
E5020 | Install rock North | 0 | 116189 | 72381 | 0 | 0 | 483527 | 0 | 0 | 672097
G1100 | Access track improvement | 0 | 16776 | 8009 | 0 | 0 | 40529 | 14765 | 0 | 80079
E5030 | Detailed earthworks South | 0 | 41755 | 22138 | 0 | 0 | 0 | 32981 | 0 | 96874
E5041 | Detailed earthworks North | 0 | 6001 | 2744 | 6322 | 0 | 90026 | 0 | 0 | 105093
| Viaduct | 0 | 3771278 | 320829 | 1955634 | 3360090 | 2779930 | 2482209 | 0 | 14669970
| Piling | 0 | 4793 | 1904 | 258431 | 217997 | 0 | 622412 | 0 | 1105537
H1080 | Piling A | 0 | 0 | 0 | 0 | 0 | 0 | 388610 | 0 | 388610
H1090 | Piling B | 0 | 0 | 0 | 0 | 217997 | 0 | 86281 | 0 | 304278
H1100 | Piling C | 0 | 0 | 0 | 258431 | 0 | 0 | 141245 | 0 | 399676
H1110 | Geotechnical drilling | 0 | 0 | 0 | 0 | 0 | 0 | 6276 | 0 | 6276
H1120 | Trim piles | 0 | 4793 | 1904 | 0 | 0 | 0 | 0 | 0 | 6697
| Abutments | 0 | 109124 | 10538 | 46263 | 33602 | 16237 | 0 | 0 | 215764
E1028 | Abutment excavation | 0 | 8369 | 9312 | 0 | 0 | 0 | 0 | 0 | 17681
C1010 | Abutment mass concrete | 0 | 800 | 0 | 3804 | 0 | 43 | 0 | 0 | 4647
S2010 | Abutment reinforcement | 0 | 15244 | 0 | 0 | 33438 | 0 | 0 | 0 | 48682
C2010 | Steel dowel | 0 | 1531 | 0 | 0 | 164 | 0 | 0 | 0 | 1695
F1010 | Abutment formwork | 0 | 76066 | 1226 | 0 | 0 | 15144 | 0 | 0 | 92436
C1041 | Abutment | 0 | 6538 | 0 | 39320 | 0 | 967 | 0 | 0 | 46825
C1042 | Slabs | 0 | 576 | 0 | 3139 | 0 | 83 | 0 | 0 | 3798
| Pile caps | 0 | 644857 | 136442 | 278563 | 864731 | 72305 | 21085 | 0 | 2017983
E4052 | Detailed earthworks 1 | 0 | 16290 | 8416 | 0 | 0 | 0 | 19127 | 0 | 43833
E4053 | Detailed earthworks 2 | 0 | 13820 | 11180 | 0 | 0 | 0 | 0 | 0 | 25000
E4054 | Detailed earthworks 3 | 0 | 8359 | 1153 | 0 | 0 | 0 | 0 | 0 | 9512
E4055 | Detailed earthworks 4 | 0 | 1434 | 821 | 0 | 0 | 0 | 1958 | 0 | 4213
F1050 | Pile cap formwork | 0 | 62012 | 19979 | 0 | 0 | 653 | 0 | 0 | 82644
S2070 | Pile cap reinforcement | 0 | 113861 | 0 | 0 | 268282 | 0 | 0 | 0 | 382143
C1052 | Pile caps | 0 | 16676 | 0 | 243505 | 0 | 7920 | 0 | 0 | 268101
C1053 | Crane pad | 0 | 19221 | 0 | 35058 | 32982 | 1166 | 0 | 0 | 88427
F1060 | Pier formwork A | 0 | 100373 | 94893 | 0 | 0 | 7799 | 0 | 0 | 203065
F1070 | Pier formwork B | 0 | 0 | 0 | 0 | 0 | 54767 | 0 | 0 | 54767
S2080 | Pier reinforcement | 0 | 292811 | 0 | 0 | 563467 | 0 | 0 | 0 | 856278
| Piers | 0 | 2783877 | 171342 | 1277729 | 2131777 | 1534420 | 1838712 | 0 | 9737857
F1080 | Pier formwork | 0 | 409662 | 65652 | 0 | 149203 | 273055 | 0 | 0 | 897572
S2090 | Diaphragm reinforcement | 0 | 148026 | 0 | 0 | 224977 | 0 | 0 | 0 | 373003
C1055 | Piers | 0 | 40611 | 0 | 191895 | 0 | 6485 | 0 | 0 | 238991
J1040 | Temporary lighting | 0 | 13269 | 0 | 0 | 0 | 24340 | 0 | 0 | 37609
S1010 | Maintenance access | 0 | 9392 | 0 | 0 | 0 | 37932 | 0 | 0 | 47324
F1020 | General formwork | 0 | 151711 | 6232 | 0 | 0 | 884733 | 0 | 0 | 1042676
F1030 | General formwork | 0 | 769551 | 0 | 0 | 0 | 31635 | 0 | 0 | 801186
F1040 | Span formwork | 0 | 166832 | 0 | 0 | 0 | 227942 | 0 | 0 | 394774
S2040 | Deck reinforcement | 0 | 513398 | 0 | 0 | 1255334 | 0 | 0 | 0 | 1768732
T1020 | Post tensioning | 0 | 0 | 0 | 0 | 502263 | 0 | 1838712 | 0 | 2340975
C2031 | Deck segments | 0 | 514311 | 99458 | 1085834 | 0 | 30285 | 0 | 0 | 1729888
C1072 | Cast fittings | 0 | 47114 | 0 | 0 | 0 | 18013 | 0 | 0 | 65127
| Parapets and crash rails | 0 | 180255 | 0 | 83889 | 99669 | 1011778 | 0 | 0 | 1375591
C2040 | Supply and erection | 0 | 45549 | 0 | 0 | 0 | 523715 | 0 | 0 | 569264
C1051 | Infill concrete | 0 | 23659 | 0 | 83889 | 0 | 2423 | 0 | 0 | 109971
S2060 | Parapet reinforcement | 0 | 61594 | 0 | 0 | 99669 | 0 | 0 | 0 | 161263
S1020 | Traffic barrier supply | 0 | 0 | 0 | 0 | 0 | 337399 | 0 | 0 | 337399
S1030 | Traffic barrier erection | 0 | 31310 | 0 | 0 | 0 | 478 | 0 | 0 | 31788
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 147545 | 0 | 0 | 147545
S1050 | Pedestrian handrail erection | 0 | 18143 | 0 | 0 | 0 | 218 | 0 | 0 | 18361
| Expansion joint | 0 | 30912 | 351 | 0 | 0 | 142830 | 0 | 0 | 174093
X1010 | Expansion joint fabrication | 0 | 0 | 0 | 0 | 0 | 77012 | 0 | 0 | 77012
X1020 | Expansion joint installation | 0 | 13774 | 0 | 0 | 0 | 348 | 0 | 0 | 14122
S1090 | Cover plates | 0 | 488 | 0 | 0 | 0 | 1330 | 0 | 0 | 1818
J1010 | Services duct | 0 | 10618 | 0 | 0 | 0 | 10841 | 0 | 0 | 21459
S1120 | Cover plates | 0 | 6032 | 351 | 0 | 0 | 53299 | 0 | 0 | 59682
| Connecting slab | 0 | 17460 | 252 | 10759 | 12314 | 2360 | 0 | 0 | 43145
C1030 | Slabs | 0 | 4122 | 252 | 10759 | 0 | 720 | 0 | 0 | 15853
S2030 | Slab reinforcement | 0 | 6293 | 0 | 0 | 12314 | 0 | 0 | 0 | 18607
C2025 | Jointing | 0 | 3965 | 0 | 0 | 0 | 1161 | 0 | 0 | 5126
C2026 | Membrane | 0 | 2800 | 0 | 0 | 0 | 376 | 0 | 0 | 3176
C2027 | Dowel fixings | 0 | 280 | 0 | 0 | 0 | 103 | 0 | 0 | 383
| Area 2 | 0 | 112668 | 83029 | 0 | 0 | 0 | 7060 | 0 | 202757
E4012 | Bulk earthworks | 0 | 111108 | 81681 | 0 | 0 | 0 | 0 | 0 | 192789
D1010 | Clearing and grubbing | 0 | 0 | 0 | 0 | 0 | 0 | 7060 | 0 | 7060
E4041 | Remove and stockpile topsoil | 0 | 1560 | 1348 | 0 | 0 | 0 | 0 | 0 | 2908
| Bridge | 0 | 1320718 | 262176 | 1010773 | 1467379 | 801495 | 843674 | 1489 | 5707704
| Piling | 0 | 4287 | 1870 | 83241 | 64606 | 0 | 176385 | 0 | 330389
H1120 | Trim piles | 0 | 2041 | 951 | 0 | 0 | 0 | 0 | 0 | 2992
H1010 | Piling 1 | 0 | 1030 | 456 | 0 | 0 | 0 | 9905 | 0 | 11391
H1020 | Piling 2 | 0 | 1216 | 463 | 0 | 0 | 0 | 103420 | 0 | 105099
H1030 | Piling 3 | 0 | 0 | 0 | 0 | 5795 | 0 | 2278 | 0 | 8073
H1040 | Piling 4 | 0 | 0 | 0 | 0 | 58811 | 0 | 19276 | 0 | 78087
H1050 | Piling 5 | 0 | 0 | 0 | 8477 | 0 | 0 | 3947 | 0 | 12424
H1060 | Piling 6 | 0 | 0 | 0 | 74764 | 0 | 0 | 34457 | 0 | 109221
H1070 | Geotechnical drilling | 0 | 0 | 0 | 0 | 0 | 0 | 3102 | 0 | 3102
| Substructure | 0 | 102296 | 1919 | 47365 | 34961 | 15221 | 0 | 0 | 201762
E1028 | Abutment excavation | 0 | 782 | 771 | 0 | 0 | 0 | 0 | 0 | 1553
C1010 | Abutment mass concrete | 0 | 1793 | 0 | 8680 | 0 | 77 | 0 | 0 | 10550
F1010 | Abutment formwork | 0 | 77595 | 1148 | 0 | 0 | 14180 | 0 | 0 | 92923
C1020 | Abutments | 0 | 5733 | 0 | 38685 | 0 | 964 | 0 | 0 | 45382
S2010 | Abutment reinforcement | 0 | 14969 | 0 | 0 | 34794 | 0 | 0 | 0 | 49763
C2010 | Steel dowel | 0 | 1424 | 0 | 0 | 167 | 0 | 0 | 0 | 1591
| Pier columns | 0 | 337687 | 91826 | 323009 | 396991 | 56167 | 22074 | 0 | 1227754
E7010 | Anchors | 0 | 3653 | 0 | 0 | 0 | 1718 | 6384 | 0 | 11755
S2050 | Minor reinforcing | 0 | 538 | 0 | 0 | 1912 | 0 | 0 | 0 | 2450
E4013 | Detailed earthworks | 0 | 14497 | 4133 | 0 | 0 | 3629 | 15690 | 0 | 37949
C1064 | Mass concrete | 0 | 157 | 320 | 848 | 0 | 7 | 0 | 0 | 1332
S2110 | Column reinforcement | 0 | 135495 | 0 | 0 | 395079 | 13200 | 0 | 0 | 543774
C1065 | Mass concrete | 0 | 75332 | 0 | 322161 | 0 | 3449 | 0 | 0 | 400942
F1110 | Pier formwork | 0 | 106763 | 87373 | 0 | 0 | 6100 | 0 | 0 | 200236
X1030 | Bearings | 0 | 1252 | 0 | 0 | 0 | 28064 | 0 | 0 | 29316
| Concrete | 0 | 713708 | 164135 | 507800 | 920432 | 406856 | 645215 | 1489 | 3359635
F1100 | General formwork | 0 | 160036 | 30175 | 0 | 49556 | 86264 | 0 | 0 | 326031
S2130 | Segment reinforcement | 0 | 235358 | 0 | 0 | 531624 | 21443 | 0 | 0 | 788425
T1010 | Prestressing | 0 | 14522 | 0 | 0 | 183368 | 2479 | 645215 | 0 | 845584
C1071 | Mass concrete | 0 | 120236 | 16853 | 464781 | 0 | 11144 | 0 | 0 | 613014
C1072 | Cast fittings | 0 | 18057 | 0 | 0 | 0 | 8381 | 0 | 0 | 26438
P1070 | Additional specialised plant | 0 | 15564 | 8935 | 0 | 88487 | 1816 | 0 | 0 | 114802
S1130 | Construction frames | 0 | 45596 | 26439 | 0 | 23968 | 36091 | 0 | 1489 | 133583
P1060 | Alternative construction strategy | 0 | 43465 | 81733 | 0 | 2110 | 1890 | 0 | 0 | 129198
C2040 | Supply and erection | 0 | 20785 | 0 | 0 | 0 | 236037 | 0 | 0 | 256822
C1051 | Infill concrete | 0 | 11538 | 0 | 43019 | 0 | 1311 | 0 | 0 | 55868
S2060 | Parapet reinforcement | 0 | 28551 | 0 | 0 | 41319 | 0 | 0 | 0 | 69870
| Barriers | 0 | 16893 | 0 | 0 | 0 | 146079 | 0 | 0 | 162972
S1020 | Traffic barrier supply | 0 | 0 | 0 | 0 | 0 | 145856 | 0 | 0 | 145856
S1030 | Traffic barrier erection | 0 | 16893 | 0 | 0 | 0 | 223 | 0 | 0 | 17116
| Pedestrian barriers | 0 | 8419 | 0 | 0 | 0 | 72247 | 0 | 0 | 80666
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 72149 | 0 | 0 | 72149
S1050 | Pedestrian handrail erection | 0 | 8419 | 0 | 0 | 0 | 98 | 0 | 0 | 8517
| Expansion joint | 0 | 17817 | 0 | 0 | 0 | 88421 | 0 | 0 | 106238
X1010 | Expansion joint fabrication | 0 | 0 | 0 | 0 | 0 | 85125 | 0 | 0 | 85125
X1020 | Expansion joint installation | 0 | 15073 | 0 | 0 | 0 | 344 | 0 | 0 | 15417
S1090 | Cover plates | 0 | 242 | 0 | 0 | 0 | 698 | 0 | 0 | 940
J1010 | Services duct | 0 | 2502 | 0 | 0 | 0 | 2254 | 0 | 0 | 4756
| Connecting slab | 0 | 19155 | 261 | 9326 | 18467 | 2320 | 0 | 0 | 49529
C1030 | Slabs | 0 | 3942 | 261 | 9326 | 0 | 682 | 0 | 0 | 14211
S2030 | Slab reinforcement | 0 | 7987 | 0 | 0 | 18467 | 0 | 0 | 0 | 26454
C2025 | Jointing | 0 | 4488 | 0 | 0 | 0 | 1162 | 0 | 0 | 5650
C2026 | Membrane | 0 | 2474 | 0 | 0 | 0 | 364 | 0 | 0 | 2838
C2027 | Dowel fixings | 0 | 264 | 0 | 0 | 0 | 112 | 0 | 0 | 376
| Abutments | 0 | 100456 | 2165 | 40032 | 31922 | 14184 | 0 | 0 | 188759
E1028 | Abutment excavation | 0 | 1137 | 1003 | 0 | 0 | 0 | 0 | 0 | 2140
C1010 | Abutment mass concrete | 0 | 655 | 0 | 3055 | 0 | 36 | 0 | 0 | 3746
F1010 | Abutment formwork | 0 | 75334 | 1162 | 0 | 0 | 13103 | 0 | 0 | 89599
C1020 | Abutments | 0 | 6483 | 0 | 36977 | 0 | 1045 | 0 | 0 | 44505
S2010 | Abutment reinforcement | 0 | 13915 | 0 | 0 | 31541 | 0 | 0 | 0 | 45456
C2010 | Steel dowel | 0 | 2932 | 0 | 0 | 381 | 0 | 0 | 0 | 3313
| Superstructure | 0 | 112901 | 7570 | 54972 | 78993 | 239166 | 0 | 0 | 493602
| Girders | 0 | 1740 | 683 | 0 | 0 | 131523 | 0 | 0 | 133946
C2011 | Manufacture beams | 0 | 0 | 0 | 0 | 0 | 130116 | 0 | 0 | 130116
C2012 | Delivery and handling | 0 | 0 | 0 | 0 | 0 | 1145 | 0 | 0 | 1145
C2013 | Erection | 0 | 1740 | 683 | 0 | 0 | 262 | 0 | 0 | 2685
| Bearings | 0 | 1480 | 0 | 0 | 0 | 31381 | 0 | 0 | 32861
X1030 | Bearings | 0 | 1480 | 0 | 0 | 0 | 31381 | 0 | 0 | 32861
| Deck fit out | 0 | 43298 | 2610 | 9117 | 24201 | 18689 | 0 | 0 | 97915
C2021 | Parapets | 0 | 25380 | 2610 | 9117 | 2090 | 6717 | 0 | 0 | 45914
S2020 | Deck reinforcement | 0 | 9903 | 0 | 0 | 22111 | 0 | 0 | 0 | 32014
C2022 | Conduit | 0 | 816 | 0 | 0 | 0 | 423 | 0 | 0 | 1239
C2024 | Jointing | 0 | 7199 | 0 | 0 | 0 | 11549 | 0 | 0 | 18748
| Traffic barriers | 0 | 2359 | 0 | 0 | 0 | 23608 | 0 | 0 | 25967
S1020 | Traffic barrier supply | 0 | 0 | 0 | 0 | 0 | 23577 | 0 | 0 | 23577
S1030 | Traffic barrier erection | 0 | 2359 | 0 | 0 | 0 | 31 | 0 | 0 | 2390
| Pedestrian barriers | 0 | 1163 | 0 | 0 | 0 | 9891 | 0 | 0 | 11054
S1040 | Pedestrian handrail supply | 0 | 0 | 0 | 0 | 0 | 9874 | 0 | 0 | 9874
S1050 | Pedestrian handrail erection | 0 | 1163 | 0 | 0 | 0 | 17 | 0 | 0 | 1180
| Expansion joint | 0 | 2019 | 0 | 0 | 0 | 8844 | 0 | 0 | 10863
C2023 | Expansion joint | 0 | 1013 | 0 | 0 | 0 | 6797 | 0 | 0 | 7810
S1090 | Cover plates | 0 | 458 | 0 | 0 | 0 | 1443 | 0 | 0 | 1901
J1010 | Services duct | 0 | 548 | 0 | 0 | 0 | 604 | 0 | 0 | 1152
| Connecting slab 1 | 0 | 28120 | 576 | 21815 | 33551 | 2828 | 0 | 0 | 86890
C1030 | Slabs | 0 | 8413 | 576 | 21815 | 0 | 1320 | 0 | 0 | 32124
S2030 | Slab reinforcement | 0 | 13577 | 0 | 0 | 33551 | 0 | 0 | 0 | 47128
C2025 | Jointing | 0 | 3306 | 0 | 0 | 0 | 931 | 0 | 0 | 4237
C2026 | Membrane | 0 | 2408 | 0 | 0 | 0 | 395 | 0 | 0 | 2803
C2027 | Dowel fixings | 0 | 416 | 0 | 0 | 0 | 182 | 0 | 0 | 598
| Connecting slab 2 | 0 | 32722 | 3701 | 24040 | 21241 | 12402 | 0 | 0 | 94106
C1030 | Slabs | 0 | 8909 | 539 | 24040 | 0 | 1532 | 0 | 0 | 35020
S2030 | Slab reinforcement | 0 | 10323 | 0 | 0 | 21241 | 0 | 0 | 0 | 31564
C2025 | Jointing | 0 | 4134 | 0 | 0 | 0 | 1159 | 0 | 0 | 5293
C2032 | Membrane | 0 | 2996 | 0 | 0 | 0 | 457 | 0 | 0 | 3453
E1026 | Retaining wall excavation | 0 | 1627 | 1082 | 0 | 0 | 0 | 0 | 0 | 2709
E1031 | Gabions and mattresses | 0 | 4733 | 2080 | 0 | 0 | 9254 | 0 | 0 | 16067
| Total | 8458570 | 10793408 | 5002457 | 4901875 | 4973734 | 6752934 | 6810515 | 8730183 | 56423676

## Estimate summary
Bulk materials
| Staff | Labour | Plant | Concrete | Steel | Other | Subcon | Other | TOTAL
Sunk costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6374775 | 6374775
Provisions | 0 | 153863 | 146669 | 1808144 | 0 | 0 | 0 | 820776 | 2929452
Establishment and preliminaries
Preliminaries time independent | 8829 | 83777 | 69473 | 443 | 0 | 137686 | 584465 | 0 | 884673
Preliminaries time related | 6114003 | 55751 | 676040 | 0 | 0 | 320000 | 84816 | 1083692 | 8334302
Direct costs
Area 1
Design | 2103961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2103961
Special plant | 0 | 2277480 | 1719349 | 0 | 0 | 499255 | 0 | 0 | 4496084
Site equipment | 0 | 868124 | 472976 | 0 | 0 | 165435 | 10522 | 449451 | 1966508
Environmental management | 231777 | 30299 | 0 | 0 | 0 | 62559 | 0 | 0 | 324635
Stormwater drainage | 0 | 2418 | 1341 | 12523 | 0 | 885 | 108691 | 0 | 125858
Earthworks | 0 | 191007 | 143782 | 0 | 0 | 0 | 799445 | 0 | 1134234
Shotcreting | 0 | 0 | 0 | 0 | 0 | 0 | 919039 | 0 | 919039
Retaining walls | 0 | 128223 | 1079 | 52090 | 0 | 277397 | 269276 | 0 | 728065
Pavement | 0 | 17537 | 14298 | 0 | 0 | 38897 | 341038 | 0 | 411770
Fencing | 0 | 0 | 0 | 0 | 0 | 0 | 84201 | 0 | 84201
Barriers | 0 | 4459 | 2476 | 0 | 0 | 0 | 83991 | 0 | 90926
Paths
Shared path North | 0 | 9721 | 516 | 740 | 0 | 22660 | 6257 | 0 | 39894
Shared path South | 0 | 2975 | 307 | 234 | 0 | 6589 | 1940 | 0 | 12045
Pedestrian areas North | 0 | 5055 | 0 | 0 | 0 | 38281 | 0 | 0 | 43336
Pedestrian areas South 1 | 0 | 8649 | 0 | 0 | 0 | 87957 | 0 | 0 | 96606
Pedestrian areas South 2 | 0 | 1947 | 0 | 0 | 0 | 15322 | 0 | 0 | 17269
Boardwalk and lookout | 0 | 41521 | 0 | 0 | 67272 | 102583 | 72950 | 0 | 284326
Signs and linemarking | 0 | 0 | 0 | 0 | 0 | 0 | 37825 | 0 | 37825
Landscaping | 0 | 6552 | 2861 | 0 | 0 | 24028 | 25370 | 0 | 58811
Access track and surrounds | 0 | 1586485 | 1077686 | 6322 | 0 | 1132809 | 47746 | 0 | 3851048
Viaduct
Piling | 0 | 4793 | 1904 | 258431 | 217997 | 0 | 622412 | 0 | 1105537
Abutments | 0 | 109124 | 10538 | 46263 | 33602 | 16237 | 0 | 0 | 215764
Pile caps | 0 | 644857 | 136442 | 278563 | 864731 | 72305 | 21085 | 0 | 2017983
Piers | 0 | 2783877 | 171342 | 1277729 | 2131777 | 1534420 | 1838712 | 0 | 9737857
Parapets and crash rails | 0 | 180255 | 0 | 83889 | 99669 | 1011778 | 0 | 0 | 1375591
Expansion joint | 0 | 30912 | 351 | 0 | 0 | 142830 | 0 | 0 | 174093
Connecting slab | 0 | 17460 | 252 | 10759 | 12314 | 2360 | 0 | 0 | 43145
Area 2 | 0 | 112668 | 83029 | 0 | 0 | 0 | 7060 | 0 | 202757
Bridge
Piling | 0 | 4287 | 1870 | 83241 | 64606 | 0 | 176385 | 0 | 330389
Substructure | 0 | 102296 | 1919 | 47365 | 34961 | 15221 | 0 | 0 | 201762
Pier columns | 0 | 337687 | 91826 | 323009 | 396991 | 56167 | 22074 | 0 | 1227754
Concrete | 0 | 713708 | 164135 | 507800 | 920432 | 406856 | 645215 | 1489 | 3359635
Barriers | 0 | 16893 | 0 | 0 | 0 | 146079 | 0 | 0 | 162972
Pedestrian barriers | 0 | 8419 | 0 | 0 | 0 | 72247 | 0 | 0 | 80666
Expansion joint | 0 | 17817 | 0 | 0 | 0 | 88421 | 0 | 0 | 106238
Connecting slab | 0 | 19155 | 261 | 9326 | 18467 | 2320 | 0 | 0 | 49529
Abutments | 0 | 100456 | 2165 | 40032 | 31922 | 14184 | 0 | 0 | 188759
Superstructure
Girders | 0 | 1740 | 683 | 0 | 0 | 131523 | 0 | 0 | 133946
Bearings | 0 | 1480 | 0 | 0 | 0 | 31381 | 0 | 0 | 32861
Deck fit out | 0 | 43298 | 2610 | 9117 | 24201 | 18689 | 0 | 0 | 97915
Traffic barriers | 0 | 2359 | 0 | 0 | 0 | 23608 | 0 | 0 | 25967
Pedestrian barriers | 0 | 1163 | 0 | 0 | 0 | 9891 | 0 | 0 | 11054
Expansion joint | 0 | 2019 | 0 | 0 | 0 | 8844 | 0 | 0 | 10863
Connecting slab 1 | 0 | 28120 | 576 | 21815 | 33551 | 2828 | 0 | 0 | 86890
Connecting slab 2 | 0 | 32722 | 3701 | 24040 | 21241 | 12402 | 0 | 0 | 94106
Total | 8458570 | 10793408 | 5002457 | 4901875 | 4973734 | 6752934 | 6810515 | 8730183 | 56423676
Check Total from Estimate sheet | 8458570 | 10793408 | 5002457 | 4901875 | 4973734 | 6752934 | 6810515 | 8730183 | 56423676
Note on B64: Dr Dale F Cooper: Note: Conditional formatting will show errors on bold red

## Risk factor allocation
Shaded cells (conditional formatting) have no cost in the estimate summary and so require no risk factors |  |  |  |  | Bulk materials
|  | Staff | Labour | Plant | Concrete | Steel | Other | Subcon | Other
| Sunk costs | [7 empty] | 100%
| Provisions |  | 108.9% | 108.9% | 108.9% |  |  |  | 108.9%
Establishment and preliminaries
| Preliminaries time independent | 104.3% | 104.3% | 104.3% | 104.3% |  | 104.3% | 104.3%
| Preliminaries time related | 119.4% | 119.4% | 119.4% |  |  | 119.4% | 119.4% | 119.4%
Direct costs
Area 1
| Design | 106.6%
| Special plant |  | 126.1% | 118.1% |  |  | 113.5%
| Site equipment |  | 126.1% | 118.1% |  |  | 113.5% | 108.7% | 122.1%
| Environmental management | 106.6% | 118.4% |  |  |  | 106.5%
| Stormwater drainage |  | 118.4% | 110.9% | 104.3% |  | 106.6% | 102.1%
| Earthworks |  | 118.4% | 110.9% |  |  |  | 102.1%
| Shotcreting |  | 118.4% |  |  |  |  | 102.1%
| Retaining walls |  | 120.9% | 113.2% | 108.8% |  | 108.8% | 104.2%
| Pavement |  | 113.5% | 106.3% |  |  | 102.2% | 97.85%
| Fencing |  | 118.5% | 111.1% |  |  |  | 102.2%
| Barriers |  | 118.5% | 111.1% |  |  |  | 102.2%
Paths
| Shared path North |  | 118.4% | 110.9% | 106.6% |  | 106.6% | 102.1%
| Shared path South |  | 118.4% | 110.9% | 106.6% |  | 106.6% | 102.1%
| Pedestrian areas North |  | 118.4% |  |  |  | 106.6%
| Pedestrian areas South 1 |  | 118.4% |  |  |  | 106.6%
| Pedestrian areas South 2 |  | 118.4% |  |  |  | 106.6%
| Boardwalk and lookout |  | 118.4% |  |  | 104.3% | 106.6% | 102.1%
| Signs and linemarking | [6 empty] | 102.1%
| Landscaping |  | 118.4% | 110.9% |  |  | 106.6% | 102.1%
| Access track and surrounds |  | 118.4% | 110.9% | 106.6% |  | 106.6% | 102.1%
Viaduct
| Piling |  | 118.4% | 110.9% | 106.6% | 104.3% |  | 102.1%
| Abutments |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Pile caps |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3% | 99.95%
| Piers |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3% | 99.95%
| Parapets and crash rails |  | 115.9% |  | 104.3% | 102.2% | 104.3%
| Expansion joint |  | 115.9% | 108.6% |  |  | 104.3%
| Connecting slab |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Area 2 |  | 118.4% | 110.9% |  |  |  | 102.1%
Bridge
| Piling |  | 118.4% | 110.9% | 106.6% | 104.3% |  | 102.1%
| Substructure |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Pier columns |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3% | 99.95%
| Concrete |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3% | 99.95% | 105.6%
| Barriers |  | 118.5% |  |  |  | 106.7%
| Pedestrian barriers |  | 118.5% |  |  |  | 106.7%
| Expansion joint |  | 115.9% |  |  |  | 104.3%
| Connecting slab |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Abutments |  | 115.9% | 108.6% | 104.3% | 102.2% | 102.2%
Superstructure
| Girders |  | 115.9% | 108.6% |  |  | 104.3%
| Bearings |  | 115.9% |  |  |  | 104.3%
| Deck fit out |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Traffic barriers |  | 118.5% |  |  |  | 106.7%
| Pedestrian barriers |  | 118.5% |  |  |  | 106.7%
| Expansion joint |  | 115.9% |  |  |  | 104.3%
| Connecting slab 1 |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
| Connecting slab 2 |  | 115.9% | 108.6% | 104.3% | 102.2% | 104.3%
Note on J12: Dr Stephen Grey: weighted average of variation in other items in this line
Note on J44: Dr Stephen Grey: weighted average of variation in other items in this line

## Schedule model
Finish Date | Entire Plan | Range Analysis - Trial Run.plan |  |  | Paste PRA CSV file contents, or equivalent, into cell A1 then adjust the formulae in columns D and E to cover the number of entries in columns A:C
Date | Hits | Cumulative Hits | Duration
2018-12-02 | 1 | 1 | 519 | 0.1% |  | Nominal start | 2017-07-01
2018-12-08 | 1 | 2 | 525 | 0.2% |  | Deterministic end | 2018-12-15
2018-12-08 | 1 | 3 | 525 | 0.3%
2018-12-14 | 1 | 4 | 531 | 0.4% |  | Deterministic duration (days) | 532
2018-12-20 | 1 | 5 | 537 | 0.5%
2018-12-20 | 1 | 6 | 537 | 0.6% |  | Entire plan duration | 608.7209
2018-12-20 | 1 | 7 | 537 | 0.7%
2018-12-20 | 1 | 8 | 537 | 0.8% |  | P10 | 608.7209 | 2019-03-01 17:18
2018-12-22 | 1 | 9 | 539 | 0.9% |  | Mean | 608.7209 | 2019-03-01 17:18
2018-12-26 | 1 | 10 | 543 | 1% |  | Median | 608.7209 | 2019-03-01 17:18
2018-12-26 | 1 | 11 | 543 | 1.1% |  | P90 | 608.7209 | 2019-03-01 17:18
2018-12-26 | 1 | 12 | 543 | 1.2%
2018-12-26 | 1 | 13 | 543 | 1.3% |  | Schedule Entire Plan | 114.4%
2018-12-28 | 1 | 14 | 545 | 1.4%
2018-12-28 | 2 | 16 | 545 | 1.6% |  | P10 | 114.4%
2018-12-28 | 1 | 17 | 545 | 1.7% |  | Mean | 114.4%
2018-12-28 | 1 | 18 | 545 | 1.8% |  | Median | 114.4%
2018-12-28 | 1 | 19 | 545 | 1.9% |  | P90 | 114.4%
2018-12-30 | 1 | 20 | 547 | 2%
2018-12-30 | 2 | 22 | 547 | 2.2%
2018-12-30 | 2 | 24 | 547 | 2.4%
2019-01-01 | 1 | 25 | 549 | 2.5%
2019-01-01 | 1 | 26 | 549 | 2.6%
2019-01-03 | 1 | 27 | 551 | 2.7%
2019-01-03 | 1 | 28 | 551 | 2.8%
2019-01-05 | 1 | 29 | 553 | 2.9%
2019-01-05 | 1 | 30 | 553 | 3%
2019-01-05 | 1 | 31 | 553 | 3.1%
2019-01-05 | 1 | 32 | 553 | 3.2%
2019-01-05 | 2 | 34 | 553 | 3.4%
2019-01-07 | 2 | 36 | 555 | 3.6%
2019-01-07 | 1 | 37 | 555 | 3.7%
2019-01-07 | 1 | 38 | 555 | 3.8%
2019-01-07 | 1 | 39 | 555 | 3.9%
2019-01-09 | 1 | 40 | 557 | 4%
2019-01-09 | 1 | 41 | 557 | 4.1%
2019-01-09 | 2 | 43 | 557 | 4.3%
2019-01-09 | 1 | 44 | 557 | 4.4%
2019-01-11 | 2 | 46 | 559 | 4.6%
2019-01-11 | 1 | 47 | 559 | 4.7%
2019-01-11 | 1 | 48 | 559 | 4.8%
2019-01-11 | 1 | 49 | 559 | 4.9%
2019-01-11 | 1 | 50 | 559 | 5%
2019-01-11 | 2 | 52 | 559 | 5.2%
2019-01-11 | 1 | 53 | 559 | 5.3%
2019-01-13 | 2 | 55 | 561 | 5.5%
2019-01-13 | 1 | 56 | 561 | 5.6%
2019-01-13 | 1 | 57 | 561 | 5.7%
2019-01-15 | 1 | 58 | 563 | 5.8%
2019-01-15 | 1 | 59 | 563 | 5.9%
2019-01-15 | 2 | 61 | 563 | 6.1%
2019-01-15 | 1 | 62 | 563 | 6.2%
2019-01-15 | 4 | 66 | 563 | 6.6%
2019-01-15 | 1 | 67 | 563 | 6.7%
2019-01-17 | 1 | 68 | 565 | 6.8%
2019-01-17 | 1 | 69 | 565 | 6.9%
2019-01-17 | 2 | 71 | 565 | 7.1%
2019-01-17 | 1 | 72 | 565 | 7.2%
2019-01-17 | 1 | 73 | 565 | 7.3%
2019-01-17 | 1 | 74 | 565 | 7.4%
2019-01-17 | 2 | 76 | 565 | 7.6%
2019-01-17 | 2 | 78 | 565 | 7.8%
2019-01-17 | 2 | 80 | 565 | 8%
2019-01-17 | 4 | 84 | 565 | 8.4%
2019-01-19 | 1 | 85 | 567 | 8.5%
2019-01-19 | 2 | 87 | 567 | 8.7%
2019-01-19 | 1 | 88 | 567 | 8.8%
2019-01-19 | 1 | 89 | 567 | 8.9%
2019-01-19 | 3 | 92 | 567 | 9.2%
2019-01-19 | 1 | 93 | 567 | 9.3%
2019-01-19 | 1 | 94 | 567 | 9.4%
2019-01-19 | 2 | 96 | 567 | 9.6%
2019-01-19 | 1 | 97 | 567 | 9.7%
2019-01-21 | 4 | 101 | 569 | 10.1%
2019-01-21 | 1 | 102 | 569 | 10.2%
2019-01-21 | 1 | 103 | 569 | 10.3%
2019-01-21 | 1 | 104 | 569 | 10.4%
2019-01-23 | 1 | 105 | 571 | 10.5%
2019-01-23 | 4 | 109 | 571 | 10.9%
2019-01-23 | 2 | 111 | 571 | 11.1%
2019-01-23 | 1 | 112 | 571 | 11.2%
2019-01-23 | 1 | 113 | 571 | 11.3%
2019-01-23 | 1 | 114 | 571 | 11.4%
2019-01-23 | 1 | 115 | 571 | 11.5%
2019-01-25 | 3 | 118 | 573 | 11.8%
2019-01-25 | 1 | 119 | 573 | 11.9%
2019-01-25 | 1 | 120 | 573 | 12%
2019-01-27 | 1 | 121 | 575 | 12.1%
2019-01-27 | 1 | 122 | 575 | 12.2%
2019-01-27 | 1 | 123 | 575 | 12.3%
2019-01-27 | 5 | 128 | 575 | 12.8%
2019-01-27 | 2 | 130 | 575 | 13%
2019-01-27 | 2 | 132 | 575 | 13.2%
2019-01-27 | 3 | 135 | 575 | 13.5%
2019-01-27 | 1 | 136 | 575 | 13.6%
2019-01-29 | 1 | 137 | 577 | 13.7%
2019-01-29 | 2 | 139 | 577 | 13.9%
2019-01-29 | 1 | 140 | 577 | 14%
2019-01-29 | 1 | 141 | 577 | 14.1%
2019-01-29 | 2 | 143 | 577 | 14.3%
2019-01-29 | 2 | 145 | 577 | 14.5%
2019-01-29 | 2 | 147 | 577 | 14.7%
2019-01-29 | 3 | 150 | 577 | 15%
2019-01-29 | 1 | 151 | 577 | 15.1%
2019-01-29 | 2 | 153 | 577 | 15.3%
2019-01-29 | 3 | 156 | 577 | 15.6%
2019-01-31 | 3 | 159 | 579 | 15.9%
2019-01-31 | 1 | 160 | 579 | 16%
2019-01-31 | 3 | 163 | 579 | 16.3%
2019-02-02 | 4 | 167 | 581 | 16.7%
2019-02-02 | 1 | 168 | 581 | 16.8%
2019-02-02 | 2 | 170 | 581 | 17%
2019-02-02 | 2 | 172 | 581 | 17.2%
2019-02-02 | 3 | 175 | 581 | 17.5%
2019-02-02 | 3 | 178 | 581 | 17.8%
2019-02-02 | 3 | 181 | 581 | 18.1%
2019-02-02 | 5 | 186 | 581 | 18.6%
2019-02-02 | 2 | 188 | 581 | 18.8%
2019-02-02 | 3 | 191 | 581 | 19.1%
2019-02-02 | 3 | 194 | 581 | 19.4%
2019-02-04 | 1 | 195 | 583 | 19.5%
2019-02-04 | 2 | 197 | 583 | 19.7%
2019-02-04 | 3 | 200 | 583 | 20%
2019-02-04 | 7 | 207 | 583 | 20.7%
2019-02-04 | 3 | 210 | 583 | 21%
2019-02-04 | 2 | 212 | 583 | 21.2%
2019-02-04 | 2 | 214 | 583 | 21.4%
2019-02-04 | 3 | 217 | 583 | 21.7%
2019-02-04 | 1 | 218 | 583 | 21.8%
2019-02-04 | 2 | 220 | 583 | 22%
2019-02-06 | 7 | 227 | 585 | 22.7%
2019-02-06 | 3 | 230 | 585 | 23%
2019-02-06 | 3 | 233 | 585 | 23.3%
2019-02-06 | 3 | 236 | 585 | 23.6%
2019-02-06 | 1 | 237 | 585 | 23.7%
2019-02-06 | 3 | 240 | 585 | 24%
2019-02-06 | 1 | 241 | 585 | 24.1%
2019-02-06 | 1 | 242 | 585 | 24.2%
2019-02-06 | 3 | 245 | 585 | 24.5%
2019-02-06 | 3 | 248 | 585 | 24.8%
2019-02-08 | 1 | 249 | 587 | 24.9%
2019-02-08 | 1 | 250 | 587 | 25%
2019-02-08 | 2 | 252 | 587 | 25.2%
2019-02-08 | 2 | 254 | 587 | 25.4%
2019-02-08 | 1 | 255 | 587 | 25.5%
2019-02-08 | 1 | 256 | 587 | 25.6%
2019-02-08 | 1 | 257 | 587 | 25.7%
2019-02-08 | 1 | 258 | 587 | 25.8%
2019-02-08 | 3 | 261 | 587 | 26.1%
2019-02-08 | 1 | 262 | 587 | 26.2%
2019-02-08 | 1 | 263 | 587 | 26.3%
2019-02-10 | 4 | 267 | 589 | 26.7%
2019-02-10 | 3 | 270 | 589 | 27%
2019-02-10 | 1 | 271 | 589 | 27.1%
2019-02-12 | 2 | 273 | 591 | 27.3%
2019-02-12 | 2 | 275 | 591 | 27.5%
2019-02-12 | 4 | 279 | 591 | 27.9%
2019-02-12 | 4 | 283 | 591 | 28.3%
2019-02-12 | 5 | 288 | 591 | 28.8%
2019-02-12 | 2 | 290 | 591 | 29%
2019-02-12 | 4 | 294 | 591 | 29.4%
2019-02-12 | 3 | 297 | 591 | 29.7%
2019-02-12 | 3 | 300 | 591 | 30%
2019-02-12 | 2 | 302 | 591 | 30.2%
2019-02-12 | 1 | 303 | 591 | 30.3%
2019-02-14 | 5 | 308 | 593 | 30.8%
2019-02-14 | 3 | 311 | 593 | 31.1%
2019-02-14 | 4 | 315 | 593 | 31.5%
2019-02-14 | 3 | 318 | 593 | 31.8%
2019-02-14 | 3 | 321 | 593 | 32.1%
2019-02-14 | 3 | 324 | 593 | 32.4%
2019-02-14 | 2 | 326 | 593 | 32.6%
2019-02-14 | 3 | 329 | 593 | 32.9%
2019-02-14 | 2 | 331 | 593 | 33.1%
2019-02-14 | 5 | 336 | 593 | 33.6%
2019-02-14 | 3 | 339 | 593 | 33.9%
2019-02-16 | 3 | 342 | 595 | 34.2%
2019-02-16 | 4 | 346 | 595 | 34.6%
2019-02-16 | 3 | 349 | 595 | 34.9%
2019-02-16 | 6 | 355 | 595 | 35.5%
2019-02-16 | 1 | 356 | 595 | 35.6%
2019-02-16 | 4 | 360 | 595 | 36%
2019-02-16 | 2 | 362 | 595 | 36.2%
2019-02-16 | 2 | 364 | 595 | 36.4%
2019-02-16 | 3 | 367 | 595 | 36.7%
2019-02-22 | 3 | 370 | 601 | 37%
2019-02-22 | 2 | 372 | 601 | 37.2%
2019-02-22 | 1 | 373 | 601 | 37.3%
2019-02-22 | 2 | 375 | 601 | 37.5%
2019-02-22 | 2 | 377 | 601 | 37.7%
2019-02-22 | 2 | 379 | 601 | 37.9%
2019-02-22 | 2 | 381 | 601 | 38.1%
2019-02-22 | 6 | 387 | 601 | 38.7%
2019-02-22 | 3 | 390 | 601 | 39%
2019-02-22 | 2 | 392 | 601 | 39.2%
2019-02-22 | 3 | 395 | 601 | 39.5%
2019-02-24 | 3 | 398 | 603 | 39.8%
2019-02-24 | 1 | 399 | 603 | 39.9%
2019-02-24 | 1 | 400 | 603 | 40%
2019-02-24 | 6 | 406 | 603 | 40.6%
2019-02-24 | 3 | 409 | 603 | 40.9%
2019-02-24 | 2 | 411 | 603 | 41.1%
2019-02-24 | 2 | 413 | 603 | 41.3%
2019-02-24 | 1 | 414 | 603 | 41.4%
2019-02-24 | 3 | 417 | 603 | 41.7%
2019-02-26 | 1 | 418 | 605 | 41.8%
2019-02-26 | 6 | 424 | 605 | 42.4%
2019-02-26 | 4 | 428 | 605 | 42.8%
2019-02-26 | 3 | 431 | 605 | 43.1%
2019-02-26 | 5 | 436 | 605 | 43.6%
2019-02-26 | 2 | 438 | 605 | 43.8%
2019-02-26 | 3 | 441 | 605 | 44.1%
2019-02-26 | 4 | 445 | 605 | 44.5%
2019-02-26 | 2 | 447 | 605 | 44.7%
2019-02-26 | 3 | 450 | 605 | 45%
2019-02-26 | 1 | 451 | 605 | 45.1%
2019-02-28 | 4 | 455 | 607 | 45.5%
2019-02-28 | 2 | 457 | 607 | 45.7%
2019-02-28 | 6 | 463 | 607 | 46.3%
2019-02-28 | 3 | 466 | 607 | 46.6%
2019-03-02 | 8 | 474 | 609 | 47.4%
2019-03-02 | 3 | 477 | 609 | 47.7%
2019-03-02 | 1 | 478 | 609 | 47.8%
2019-03-02 | 3 | 481 | 609 | 48.1%
2019-03-02 | 2 | 483 | 609 | 48.3%
2019-03-02 | 2 | 485 | 609 | 48.5%
2019-03-02 | 3 | 488 | 609 | 48.8%
2019-03-02 | 4 | 492 | 609 | 49.2%
2019-03-02 | 1 | 493 | 609 | 49.3%
2019-03-02 | 1 | 494 | 609 | 49.4%
2019-03-02 | 2 | 496 | 609 | 49.6%
2019-03-04 | 5 | 501 | 611 | 50.1%
2019-03-04 | 2 | 503 | 611 | 50.3%
2019-03-04 | 4 | 507 | 611 | 50.7%
2019-03-04 | 8 | 515 | 611 | 51.5%
2019-03-04 | 1 | 516 | 611 | 51.6%
2019-03-04 | 4 | 520 | 611 | 52%
2019-03-04 | 1 | 521 | 611 | 52.1%
2019-03-04 | 2 | 523 | 611 | 52.3%
2019-03-06 | 8 | 531 | 613 | 53.1%
2019-03-06 | 1 | 532 | 613 | 53.2%
2019-03-06 | 3 | 535 | 613 | 53.5%
2019-03-06 | 2 | 537 | 613 | 53.7%
2019-03-06 | 1 | 538 | 613 | 53.8%
2019-03-06 | 2 | 540 | 613 | 54%
2019-03-06 | 5 | 545 | 613 | 54.5%
2019-03-06 | 6 | 551 | 613 | 55.1%
2019-03-06 | 4 | 555 | 613 | 55.5%
2019-03-06 | 1 | 556 | 613 | 55.6%
2019-03-06 | 1 | 557 | 613 | 55.7%
2019-03-08 | 1 | 558 | 615 | 55.8%
2019-03-08 | 6 | 564 | 615 | 56.4%
2019-03-08 | 2 | 566 | 615 | 56.6%
2019-03-08 | 1 | 567 | 615 | 56.7%
2019-03-08 | 3 | 570 | 615 | 57%
2019-03-08 | 4 | 574 | 615 | 57.4%
2019-03-08 | 2 | 576 | 615 | 57.6%
2019-03-08 | 2 | 578 | 615 | 57.8%
2019-03-08 | 5 | 583 | 615 | 58.3%
2019-03-08 | 7 | 590 | 615 | 59%
2019-03-08 | 3 | 593 | 615 | 59.3%
2019-03-08 | 2 | 595 | 615 | 59.5%
2019-03-10 | 4 | 599 | 617 | 59.9%
2019-03-10 | 2 | 601 | 617 | 60.1%
2019-03-10 | 3 | 604 | 617 | 60.4%
2019-03-12 | 1 | 605 | 619 | 60.5%
2019-03-12 | 3 | 608 | 619 | 60.8%
2019-03-12 | 5 | 613 | 619 | 61.3%
2019-03-12 | 7 | 620 | 619 | 62%
2019-03-12 | 3 | 623 | 619 | 62.3%
2019-03-12 | 3 | 626 | 619 | 62.6%
2019-03-12 | 1 | 627 | 619 | 62.7%
2019-03-12 | 1 | 628 | 619 | 62.8%
2019-03-12 | 1 | 629 | 619 | 62.9%
2019-03-12 | 2 | 631 | 619 | 63.1%
2019-03-14 | 9 | 640 | 621 | 64%
2019-03-14 | 2 | 642 | 621 | 64.2%
2019-03-14 | 5 | 647 | 621 | 64.7%
2019-03-14 | 2 | 649 | 621 | 64.9%
2019-03-14 | 3 | 652 | 621 | 65.2%
2019-03-14 | 2 | 654 | 621 | 65.4%
2019-03-14 | 2 | 656 | 621 | 65.6%
2019-03-14 | 3 | 659 | 621 | 65.9%
2019-03-14 | 1 | 660 | 621 | 66%
2019-03-14 | 4 | 664 | 621 | 66.4%
2019-03-14 | 3 | 667 | 621 | 66.7%
2019-03-16 | 2 | 669 | 623 | 66.9%
2019-03-16 | 2 | 671 | 623 | 67.1%
2019-03-16 | 2 | 673 | 623 | 67.3%
2019-03-16 | 7 | 680 | 623 | 68%
2019-03-16 | 1 | 681 | 623 | 68.1%
2019-03-16 | 5 | 686 | 623 | 68.6%
2019-03-16 | 2 | 688 | 623 | 68.8%
2019-03-16 | 6 | 694 | 623 | 69.4%
2019-03-16 | 1 | 695 | 623 | 69.5%
2019-03-18 | 4 | 699 | 625 | 69.9%
2019-03-18 | 2 | 701 | 625 | 70.1%
2019-03-18 | 2 | 703 | 625 | 70.3%
2019-03-18 | 1 | 704 | 625 | 70.4%
2019-03-18 | 3 | 707 | 625 | 70.7%
2019-03-18 | 1 | 708 | 625 | 70.8%
2019-03-18 | 2 | 710 | 625 | 71%
2019-03-18 | 5 | 715 | 625 | 71.5%
2019-03-20 | 4 | 719 | 627 | 71.9%
2019-03-20 | 1 | 720 | 627 | 72%
2019-03-20 | 3 | 723 | 627 | 72.3%
2019-03-20 | 2 | 725 | 627 | 72.5%
2019-03-20 | 1 | 726 | 627 | 72.6%
2019-03-20 | 3 | 729 | 627 | 72.9%
2019-03-22 | 1 | 730 | 629 | 73%
2019-03-22 | 3 | 733 | 629 | 73.3%
2019-03-22 | 1 | 734 | 629 | 73.4%
2019-03-22 | 1 | 735 | 629 | 73.5%
2019-03-22 | 3 | 738 | 629 | 73.8%
2019-03-22 | 1 | 739 | 629 | 73.9%
2019-03-22 | 1 | 740 | 629 | 74%
2019-03-22 | 5 | 745 | 629 | 74.5%
2019-03-22 | 1 | 746 | 629 | 74.6%
2019-03-22 | 2 | 748 | 629 | 74.8%
2019-03-22 | 4 | 752 | 629 | 75.2%
2019-03-24 | 4 | 756 | 631 | 75.6%
2019-03-24 | 2 | 758 | 631 | 75.8%
2019-03-24 | 2 | 760 | 631 | 76%
2019-03-24 | 2 | 762 | 631 | 76.2%
2019-03-24 | 8 | 770 | 631 | 77%
2019-03-24 | 2 | 772 | 631 | 77.2%
2019-03-24 | 1 | 773 | 631 | 77.3%
2019-03-24 | 1 | 774 | 631 | 77.4%
2019-03-24 | 1 | 775 | 631 | 77.5%
2019-03-24 | 1 | 776 | 631 | 77.6%
2019-03-24 | 1 | 777 | 631 | 77.7%
2019-03-24 | 2 | 779 | 631 | 77.9%
2019-03-26 | 3 | 782 | 633 | 78.2%
2019-03-26 | 1 | 783 | 633 | 78.3%
2019-03-26 | 3 | 786 | 633 | 78.6%
2019-03-26 | 1 | 787 | 633 | 78.7%
2019-03-26 | 2 | 789 | 633 | 78.9%
2019-03-26 | 3 | 792 | 633 | 79.2%
2019-03-26 | 2 | 794 | 633 | 79.4%
2019-03-26 | 3 | 797 | 633 | 79.7%
2019-03-26 | 2 | 799 | 633 | 79.9%
2019-03-26 | 1 | 800 | 633 | 80%
2019-03-28 | 1 | 801 | 635 | 80.1%
2019-03-28 | 1 | 802 | 635 | 80.2%
2019-03-28 | 3 | 805 | 635 | 80.5%
2019-03-30 | 3 | 808 | 637 | 80.8%
2019-03-30 | 1 | 809 | 637 | 80.9%
2019-03-30 | 2 | 811 | 637 | 81.1%
2019-03-30 | 1 | 812 | 637 | 81.2%
2019-03-30 | 4 | 816 | 637 | 81.6%
2019-03-30 | 1 | 817 | 637 | 81.7%
2019-03-30 | 4 | 821 | 637 | 82.1%
2019-03-30 | 1 | 822 | 637 | 82.2%
2019-03-30 | 2 | 824 | 637 | 82.4%
2019-04-01 | 2 | 826 | 639 | 82.6%
2019-04-01 | 1 | 827 | 639 | 82.7%
2019-04-01 | 5 | 832 | 639 | 83.2%
2019-04-01 | 5 | 837 | 639 | 83.7%
2019-04-01 | 2 | 839 | 639 | 83.9%
2019-04-01 | 3 | 842 | 639 | 84.2%
2019-04-01 | 4 | 846 | 639 | 84.6%
2019-04-01 | 3 | 849 | 639 | 84.9%
2019-04-01 | 2 | 851 | 639 | 85.1%
2019-04-01 | 1 | 852 | 639 | 85.2%
2019-04-03 | 3 | 855 | 641 | 85.5%
2019-04-03 | 4 | 859 | 641 | 85.9%
2019-04-03 | 2 | 861 | 641 | 86.1%
2019-04-03 | 1 | 862 | 641 | 86.2%
2019-04-03 | 1 | 863 | 641 | 86.3%
2019-04-03 | 2 | 865 | 641 | 86.5%
2019-04-03 | 1 | 866 | 641 | 86.6%
2019-04-03 | 1 | 867 | 641 | 86.7%
2019-04-03 | 1 | 868 | 641 | 86.8%
2019-04-03 | 1 | 869 | 641 | 86.9%
2019-04-03 | 1 | 870 | 641 | 87%
2019-04-05 | 4 | 874 | 643 | 87.4%
2019-04-05 | 1 | 875 | 643 | 87.5%
2019-04-05 | 1 | 876 | 643 | 87.6%
2019-04-05 | 1 | 877 | 643 | 87.7%
2019-04-07 | 3 | 880 | 645 | 88%
2019-04-07 | 3 | 883 | 645 | 88.3%
2019-04-07 | 1 | 884 | 645 | 88.4%
2019-04-07 | 2 | 886 | 645 | 88.6%
2019-04-09 | 1 | 887 | 647 | 88.7%
2019-04-09 | 1 | 888 | 647 | 88.8%
2019-04-09 | 1 | 889 | 647 | 88.9%
2019-04-09 | 1 | 890 | 647 | 89%
2019-04-09 | 1 | 891 | 647 | 89.1%
2019-04-09 | 1 | 892 | 647 | 89.2%
2019-04-09 | 3 | 895 | 647 | 89.5%
2019-04-11 | 3 | 898 | 649 | 89.8%
2019-04-11 | 1 | 899 | 649 | 89.9%
2019-04-11 | 3 | 902 | 649 | 90.2%
2019-04-11 | 1 | 903 | 649 | 90.3%
2019-04-11 | 2 | 905 | 649 | 90.5%
2019-04-11 | 2 | 907 | 649 | 90.7%
2019-04-11 | 2 | 909 | 649 | 90.9%
2019-04-11 | 3 | 912 | 649 | 91.2%
2019-04-11 | 1 | 913 | 649 | 91.3%
2019-04-11 | 1 | 914 | 649 | 91.4%
2019-04-11 | 1 | 915 | 649 | 91.5%
2019-04-13 | 2 | 917 | 651 | 91.7%
2019-04-13 | 2 | 919 | 651 | 91.9%
2019-04-13 | 1 | 920 | 651 | 92%
2019-04-13 | 2 | 922 | 651 | 92.2%
2019-04-13 | 3 | 925 | 651 | 92.5%
2019-04-13 | 1 | 926 | 651 | 92.6%
2019-04-13 | 1 | 927 | 651 | 92.7%
2019-04-13 | 2 | 929 | 651 | 92.9%
2019-04-15 | 1 | 930 | 653 | 93%
2019-04-15 | 1 | 931 | 653 | 93.1%
2019-04-15 | 1 | 932 | 653 | 93.2%
2019-04-15 | 1 | 933 | 653 | 93.3%
2019-04-15 | 1 | 934 | 653 | 93.4%
2019-04-17 | 1 | 935 | 655 | 93.5%
2019-04-17 | 1 | 936 | 655 | 93.6%
2019-04-17 | 1 | 937 | 655 | 93.7%
2019-04-17 | 1 | 938 | 655 | 93.8%
2019-04-19 | 3 | 941 | 657 | 94.1%
2019-04-19 | 1 | 942 | 657 | 94.2%
2019-04-19 | 1 | 943 | 657 | 94.3%
2019-04-19 | 1 | 944 | 657 | 94.4%
2019-04-19 | 1 | 945 | 657 | 94.5%
2019-04-19 | 3 | 948 | 657 | 94.8%
2019-04-21 | 1 | 949 | 659 | 94.9%
2019-04-21 | 1 | 950 | 659 | 95%
2019-04-21 | 5 | 955 | 659 | 95.5%
2019-04-21 | 2 | 957 | 659 | 95.7%
2019-04-21 | 1 | 958 | 659 | 95.8%
2019-04-21 | 1 | 959 | 659 | 95.9%
2019-04-23 | 1 | 960 | 661 | 96%
2019-04-23 | 1 | 961 | 661 | 96.1%
2019-04-23 | 1 | 962 | 661 | 96.2%
2019-04-23 | 1 | 963 | 661 | 96.3%
2019-04-23 | 1 | 964 | 661 | 96.4%
2019-04-23 | 1 | 965 | 661 | 96.5%
2019-04-25 | 2 | 967 | 663 | 96.7%
2019-04-27 | 1 | 968 | 665 | 96.8%
2019-04-27 | 1 | 969 | 665 | 96.9%
2019-04-27 | 1 | 970 | 665 | 97%
2019-04-27 | 1 | 971 | 665 | 97.1%
2019-04-27 | 1 | 972 | 665 | 97.2%
2019-04-29 | 1 | 973 | 667 | 97.3%
2019-04-29 | 1 | 974 | 667 | 97.4%
2019-04-29 | 2 | 976 | 667 | 97.6%
2019-05-01 | 1 | 977 | 669 | 97.7%
2019-05-01 | 2 | 979 | 669 | 97.9%
2019-05-01 | 1 | 980 | 669 | 98%
2019-05-03 | 1 | 981 | 671 | 98.1%
2019-05-05 | 1 | 982 | 673 | 98.2%
2019-05-07 | 1 | 983 | 675 | 98.3%
2019-05-07 | 1 | 984 | 675 | 98.4%
2019-05-07 | 2 | 986 | 675 | 98.6%
2019-05-09 | 1 | 987 | 677 | 98.7%
2019-05-09 | 1 | 988 | 677 | 98.8%
2019-05-11 | 1 | 989 | 679 | 98.9%
2019-05-11 | 2 | 991 | 679 | 99.1%
2019-05-11 | 2 | 993 | 679 | 99.3%
2019-05-15 | 1 | 994 | 683 | 99.4%
2019-05-15 | 1 | 995 | 683 | 99.5%
2019-05-17 | 2 | 997 | 685 | 99.7%
2019-05-17 | 1 | 998 | 685 | 99.8%
2019-05-17 | 1 | 999 | 685 | 99.9%
2019-05-19 | 1 | 1000 | 687 | 100%

## Model
Bulk materials
| Staff | Labour | Plant | Concrete | Steel | Other | Subcon | Other | TOTAL
Sunk costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6374775 | 6374775
Provisions | 0 | 167539.7111 | 159706.2444 | 1968867.9111 | 0 | 0 | 0 | 893733.8667 | 2929452
Establishment and preliminaries
Preliminaries time independent | 9209.9783 | 87392.0433 | 72470.8145 | 462.1158 | 0 | 143627.259 | 609685.1235 | 0 | 922847.3343
Preliminaries time related | 7297587.6074 | 66543.606 | 806911.7935 | 0 | 0 | 381947.4793 | 101235.1794 | 1293479.4617 | 9947705.1273
Direct costs
Area 1
Design | 2243249.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2243249.1991
Special plant | 0 | 2872194.769 | 2031390.4191 | 0 | 0 | 566661.226 | 0 | 0 | 5470246.414
Site equipment | 0 | 1094815.8542 | 558815.5254 | 0 | 0 | 187770.9786 | 11439.6089 | 548932.3572 | 2401774.3243
Environmental management | 247121.2963 | 35869.4434 | 0 | 0 | 0 | 66654.2582 | 0 | 0 | 349644.9979
Stormwater drainage | 0 | 2862.8936 | 1487.4684 | 13063.3773 | 0 | 943.0483 | 110942.0182 | 0 | 129298.8058
Earthworks | 0 | 226150.8358 | 159486.3351 | 0 | 0 | 0 | 816001.709 | 0 | 1201638.8799
Shotcreting | 0 | 0 | 0 | 0 | 0 | 0 | 938072.5311 | 0 | 938072.5311
Retaining walls | 0 | 154979.5515 | 1221.7995 | 56662.0149 | 0 | 301753.2697 | 280581.9165 | 0 | 795198.5521
Pavement | 0 | 19904.7683 | 15203.6254 | 0 | 0 | 39733.7624 | 333701.5019 | 0 | 408543.658
Fencing | 0 | 0 | 0 | 0 | 0 | 0 | 86051.4082 | 0 | 86051.4082
Barriers | 0 | 5285.9694 | 2749.8427 | 0 | 0 | 0 | 85836.7933 | 0 | 93872.6053
Paths
Shared path North | 0 | 11509.5901 | 572.3592 | 788.5148 | 0 | 24146.2992 | 6386.5841 | 0 | 43403.3473
Shared path South | 0 | 3522.3774 | 340.5315 | 249.3412 | 0 | 7021.1812 | 1980.1779 | 0 | 13113.6091
Pedestrian areas North | 0 | 5985.0816 | 0 | 0 | 0 | 40791.9012 | 0 | 0 | 46776.9827
Pedestrian areas South 1 | 0 | 10240.3502 | 0 | 0 | 0 | 93726.2154 | 0 | 0 | 103966.5656
Pedestrian areas South 2 | 0 | 2305.2332 | 0 | 0 | 0 | 16326.9901 | 0 | 0 | 18632.2233
Boardwalk and lookout | 0 | 49160.5483 | 0 | 0 | 70174.8396 | 109311.5539 | 74460.813 | 0 | 303107.7549
Signs and linemarking | 0 | 0 | 0 | 0 | 0 | 0 | 38608.3654 | 0 | 38608.3654
Landscaping | 0 | 7757.5182 | 3173.4877 | 0 | 0 | 25604.0281 | 25895.4191 | 0 | 62430.4531
Access track and surrounds | 0 | 1878386.1783 | 1195394.3507 | 6736.4734 | 0 | 1207111.4328 | 48734.8318 | 0 | 4336363.267
Viaduct
Piling | 0 | 5674.8756 | 2111.961 | 275373.8603 | 227403.7417 | 0 | 635302.3106 | 0 | 1145866.7491
Abutments | 0 | 126521.894 | 11446.5246 | 48273.4558 | 34324.855 | 16943.1032 | 0 | 0 | 237509.8327
Pile caps | 0 | 747668.0568 | 148205.2297 | 290668.5403 | 883333.3181 | 75449.349 | 21075.2423 | 0 | 2166399.7364
Piers | 0 | 3227717.0085 | 186114.1033 | 1333255.3978 | 2177636.3411 | 1601147.7788 | 1837861.0858 | 0 | 10363731.7152
Parapets and crash rails | 0 | 208993.4754 | 0 | 87534.5727 | 101813.1054 | 1055777.4907 | 0 | 0 | 1454118.6443
Expansion joint | 0 | 35840.3723 | 381.2612 | 0 | 0 | 149041.2907 | 0 | 0 | 185262.9242
Connecting slab | 0 | 20243.6886 | 273.726 | 11226.5549 | 12578.902 | 2462.63 | 0 | 0 | 46785.5015
Area 2 | 0 | 112668 | 83029 | 0 | 0 | 0 | 7060 | 0 | 202757
Bridge
Piling | 0 | 5075.7754 | 2074.2474 | 88698.3199 | 67393.7996 | 0 | 180037.9781 | 0 | 343280.1205
Substructure | 0 | 118605.2901 | 2084.4449 | 49423.3456 | 35713.0901 | 15882.9202 | 0 | 0 | 221709.0909
Pier columns | 0 | 391525.2267 | 99742.6997 | 337046.0346 | 405531.1736 | 58609.551 | 22063.7847 | 0 | 1314518.4703
Concrete | 0 | 827496.1324 | 178285.7579 | 529867.5157 | 940232.5725 | 424549.0678 | 644916.4091 | 1572.005 | 3546919.4606
Barriers | 0 | 20025.988 | 0 | 0 | 0 | 155853.5556 | 0 | 0 | 175879.5436
Pedestrian barriers | 0 | 9980.3938 | 0 | 0 | 0 | 77081.2494 | 0 | 0 | 87061.6432
Expansion joint | 0 | 20657.6059 | 0 | 0 | 0 | 92266.1903 | 0 | 0 | 112923.7962
Connecting slab | 0 | 22208.9264 | 283.5019 | 9731.2809 | 18864.2669 | 2420.8905 | 0 | 0 | 53508.8666
Abutments | 0 | 116471.9346 | 2351.6536 | 41771.6747 | 32608.7144 | 14489.1299 | 0 | 0 | 207693.1071
Superstructure
Girders | 0 | 2017.4123 | 741.8843 | 0 | 0 | 137242.5798 | 0 | 0 | 140001.8763
Bearings | 0 | 1715.9599 | 0 | 0 | 0 | 32745.6749 | 0 | 0 | 34461.6347
Deck fit out | 0 | 50201.1012 | 2835.0189 | 9513.1984 | 24721.6182 | 19501.7341 | 0 | 0 | 106772.6708
Traffic barriers | 0 | 2796.5018 | 0 | 0 | 0 | 25187.6775 | 0 | 0 | 27984.1793
Pedestrian barriers | 0 | 1378.6908 | 0 | 0 | 0 | 10552.8346 | 0 | 0 | 11931.5254
Expansion joint | 0 | 2340.8939 | 0 | 0 | 0 | 9228.6017 | 0 | 0 | 11569.4955
Connecting slab 1 | 0 | 32603.2372 | 625.6593 | 22763.0167 | 34272.7578 | 2950.9821 | 0 | 0 | 93215.6531
Connecting slab 2 | 0 | 37938.9448 | 4020.0785 | 25084.7087 | 21697.9419 | 12941.3295 | 0 | 0 | 101683.0035
Noise walls required at southern end | [8 empty] | 0
Total | 9797168.081 | 12850773.7092 | 5733531.3495 | 5207061.2255 | 5088301.0379 | 7205456.4947 | 6917930.7918 | 9112492.6906 | 61652319.6468

## Risk factors
Variation
Description | Optimistic | Likely | Pessimistic | Simulated | Factor | Excel name
Provisions | 0% | 0% | 20% | 8.889% | 108.9% | Provisions
Preliminaries rate | -5% | 0% | 15% | 4.315% | 104.3% | Prelim_running
Duration |  |  |  |  | 114.4% | Duration
Engineering scale | -10% | 0% | 20% | 4.302% | 104.3% | Q_Eng
Plant and site equipment quantity | 0% | 0% | 25% | 11.11% | 111.1% | Q_Plant
Earthworks quantity | -5% | 0% | 15% | 4.315% | 104.3% | Q_Earth
Concrete quantity | -5% | 0% | 10% | 2.151% | 102.2% | Q_Conc
Retaining walls quantity | -5% | 0% | 20% | 6.489% | 106.5% | Q_Walls
Pavement quantity | -5% | 0% | 5% | 0% | 100% | Q_Pave
Barriers quantity | 0% | 0% | 10% | 4.444% | 104.4% | Q_Barrier
Piling quantity | -5% | 0% | 15% | 4.315% | 104.3% | Q_Pile
Structural steel quantity | -5% | 0% | 10% | 2.151% | 102.2% | Q_Steel | @RISK Correlations | Concrete rate in $E$15 | Steel rate in $E$16 | General bulks rate in $E$17 | Plant rate in $E$18 | Subcontract rates in $E$19
Concrete rate | -10% | 0% | 15% | 2.148% | 102.1% | R_Conc | Concrete rate in $E$15 | 1
Steel rate | -10% | 0% | 10% | 0% | 100% | R_Steel | Steel rate in $E$16 | 1 | 1
General bulks rate | -5% | 0% | 10% | 2.151% | 102.2% | R_General | General bulks rate in $E$17 | 1 | 1 | 1
Plant rate | -10% | 0% | 5% | -2.151% | 97.85% | R_Plant | Plant rate in $E$18 | 1 | 1 | 1 | 1
Subcontract rates | -10% | 0% | 5% | -2.151% | 97.85% | R_Subcon | Subcontract rates in $E$19 | 1 | 1 | 1 | 1 | 1
Staff rate | 0% | 0% | 5% | 2.222% | 102.2% | R_Staff
Labour rate | 0% | 0% | 10% | 4.444% | 104.4% | R_Labour
Productivity | -5% | 0% | 25% | 8.672% | 108.7% | Productivity
Major risks
Noise walls required at southern end |  |  | Net impact | 0
Impact | 0.5 | 1.2 | 2 | 1.2429
Occurrence | Prob = | 15% |  | 0
Note on I14: @RISK Correlation Market_rates Updated: 10/06/2016 4:34:53 PM

## RiskSerializationData (hidden)
0 | 0
0
0
FALSE | 15680 | 7345 | 26560 | 100
FALSE | 15680 | 7345 | 26560 | 500
FALSE | 15680 | 7345 | 26560 | 1000
FALSE | 15680 | 7345 | 26560 | 1500
FALSE | 15680 | 7345 | 26560 | 2000
0
0 | FALSE | FALSE | 10 | 0.95 | 1

## Summary output
[5 empty] | Percentile | Risk of exceeding target
|  |  |  | 0% | 61.6523 | 100%
|  |  |  | 1% | 61.6523 | 99%
|  |  |  | 2% | 61.6523 | 98%
|  |  |  | 3% | 61.6523 | 97%
|  |  |  | 4% | 61.6523 | 96%
|  |  |  | 5% | 61.6523 | 95%
|  |  |  | 6% | 61.6523 | 94%
|  |  |  | 7% | 61.6523 | 93%
|  |  |  | 8% | 61.6523 | 92%
|  |  |  | 9% | 61.6523 | 91%
|  |  |  | 10% | 61.6523 | 90%
|  |  |  | 15% | 61.6523 | 85%
|  |  |  | 20% | 61.6523 | 80%
|  |  |  | 25% | 61.6523 | 75%
|  |  |  | 30% | 61.6523 | 70%
|  |  |  | 35% | 61.6523 | 65%
|  |  |  | 40% | 61.6523 | 60%
|  |  |  | 45% | 61.6523 | 55%
|  |  |  | 50% | 61.6523 | 50%
|  |  |  | 55% | 61.6523 | 45%
|  |  |  | 60% | 61.6523 | 40%
|  |  |  | 65% | 61.6523 | 35%
Total | 61.6523 | Place link to simulated value here |  | 70% | 61.6523 | 30%
|  |  |  | 75% | 61.6523 | 25%
Summary output |  | Variation |  | 80% | 61.6523 | 20%
P10 | 61.6523 | 9.267% | 5.2286 | 85% | 61.6523 | 15%
P50 | 61.6523 | 9.267% | 5.2286 | 90% | 61.6523 | 10%
P90 | 61.6523 | 9.267% | 5.2286 | 91% | 61.6523 | 9%
Base | 56.4237 | Place link to base value here |  | 92% | 61.6523 | 8%
|  |  |  | 93% | 61.6523 | 7%
|  |  |  | 94% | 61.6523 | 6%
|  |  |  | 95% | 61.6523 | 5%
|  |  |  | 96% | 61.6523 | 4%
|  |  |  | 97% | 61.6523 | 3%
|  |  |  | 98% | 61.6523 | 2%
|  |  |  | 99% | 61.6523 | 1%
|  |  |  | 100% | 61.6523 | 0%
Chart markers
P10
[5 empty] | 61.6523 | 1
[5 empty] | 61.6523 | 0
P50
[5 empty] | 61.6523 | 1
[5 empty] | 61.6523 | 0
P90
[5 empty] | 61.6523 | 1
[5 empty] | 61.6523 | 0
Base
[5 empty] | 56.4237 | 1
[5 empty] | 56.4237 | 0